## Sheet1
| Phases | Staff required | Technical Resources | Cost | Hours/Month | Total | Contingency Budget
1 | Project Initiation | 1.Project Manager(1) |  | $75/hour | 40 | $3000 | 10%
|  | 2.Stakeholder Analyst(2) |  | $60/hour | 30 | $1800
|  |  | 3.Basic office equipment |  |  | $5000
|  |  | 4.Collaboration Tools | $200/month | 3 months | $600
| Total Initiation Phase Cost(A) |  |  |  |  | $10,400 | $1,040
2 | Research and Requirement Analysis
|  | 1.Business Analysts(2) |  | $65/hour | 50 | $3,250 | 8%
|  | 2.Data Analyst(1) |  | $55/hour | 40 | $2,200
|  |  | 3.Data Analysis Tools | $300/month | 3 months | $900
|  |  | 4.Collaboration Platforms | $150/month | 3 months | $450
| Total Research and Requirement Analysis Cost(B) |  |  |  |  | $6,800 | $544
3 | Data Collection and Preprocessing
|  | 1.Data Scientists(2) |  | $80/hour | 60 | $4,800 | 10%
|  | 2.Data Engineers(1) |  | $70/hour | 40 | $2,800
|  |  | 3. Data preprocessing tools |  |  | $2000
|  |  | 4.Cloud storage | $500/month | 3 months | $1500
| Total Data Collection and Preprocessing Cost(C) |  |  |  |  | 11100 | $1,110
4 | AI Model Development
|  | 1.Machine Learning Engineers(2) |  | $90/hour | 80 | $7200 | 12%
|  | 2.Data Scientists (1) |  | $80/hour | 60 | $4,800
|  |  | 3.ML frameworks licenses |  |  | $5,000
|  |  | 4.Powerful computing resources | $800/month | 3 month | $2,400
| Total AI Model Development Cost (D) |  |  |  |  | $19,400 | $2,328
5 | User Interface Design
|  | 1.UI/UX Designers(2) |  | $70/hour | 60 | $4,200 | 8%
|  | 2.Front-end Developers(1) |  | $75/hour | 40 | $3,000
|  |  | 3.Design software licenses |  |  | $3000
|  |  | 4.Development tools licenses |  |  | $2,500
| Total User Interface Design Cost(E) |  |  |  |  | $12,700 | $1,016
6 | Integration of AI Model with UI
|  | 1.Integration Specialists(2) |  | $80/hour | 50 | $4,000 | 10%
|  | 2.Front-end Developers(1) |  | $75/hour | 40 | $3,000
|  |  | 3.Integration tools licenses |  |  | $4,000
|  |  | 4.Version control systems licenses |  |  | $1,500
| Total Integration Cost(F) |  |  |  |  | $12,500 | $1,250
7 | Testing and Quality Assurance | [5 empty] | 12%
|  | 1.QA Engineers(2) |  | $85/hour | 60 | $5,100
|  | 2.Software Testers(1) |  | $80/hour | 40 | $3,200
|  |  | 3.Testing tools licenses |  |  | $2,500
|  |  | 4.Bug tracking systems licenses |  |  | $1,200
| Total Testing and QA Cost(G) |  |  |  |  | $11,00 | $1,320
8 | Documentation and Training
|  | 1.Technical Writers(2) |  | $65/hour | 50 | $3,250 | 8%
|  | 2.Training Facilitators(1) |  | $60/hour | 30 | $1,800
|  |  | 3.Documentation tools licenses |  |  | $1,500
|  |  | 4.Training Platforms licenses |  |  | $1,000
| Total Documentation and Training Cost(H) |  |  |  |  | $7,550 | $604
9 | Deployment
|  | 1.System Architecture(2) |  | $70/hour | 50 | $3,500 | 15%
|  | 2.Deployment Specialists(1) |  | $75/hour | 40 | $3,000
|  |  | 3.Deployment tools licenses |  |  | $2,000
|  |  | 4.Server infrastrucure setup |  |  | $10,000
| Total Deployment Cost(I) |  |  |  |  | $18,500 | $2,775
10 | Monitoring and Feedback Collection
|  | 1.System Administrators(1) |  | $70/hour | 30 | $2,100 | 8%
|  | 2.Customer Support(1) |  | $65/hour | 40 | $2,600
|  |  | 3.Monitoring tools licenses |  |  | $3000
|  |  | 4.Feedback collection platform licenses |  |  | $1,500
| Total Monitoring and Feedback Collection Cost(J) |  |  |  |  | $9,200 | $736
11 | Project Review and Optimization
|  | 1.Project Manger(1) |  | $75/hour | 40 | $3,000 | 10%
|  | 2.Optimization Specialist(1) |  | $80/hour | 30 | $2,400
|  |  | 3.Evaluation tools licenses |  |  | $2,500
|  |  | 4.Optimization framworks licenses |  |  | $1,200
| Total Project Review and Optimization(K) |  |  |  |  | $9,100 | $910
L=$13,033
Grand Total Estimate=(Sum of Costs)+(Sum of Contingency Budgets)
(A+B+C+D+E+F+G+H+I+J+K+L)
Grand Total Estimate=$131,250+$13,033
Grand Total Estimate=$144,283